## List1
Attachment 1 - The Most Significant Traffic Restrictions in 2008
Traffic restriction on firs-class city roads
| Road | City District | Investor | Planned for | Type of Action | Restriction extent | Impact on Traffic | Priority
1 | Anglicka Str. between Namesti Miru and Belehradska | 2 | TSK HMP | July 1st - Aug 28th 2008 | road reconstruction | ½ closure, 2 lanes always preserved | medium -lower capacity of the road | 2
2 | Sokolovska Str. between I.P. Pavlova and Tyrsova | 2 | PVK a.s. | July 1st - Aug 29th 2008 | sewerage repairs | closure of right lane in place of entrance shafts | medium -lower capacity of the road | 3
3 | Vysehradsky Tunnel, Rasin and Podoli Quay near the tunnel | 2 | PVS a.s., PPD a.s., TSK HMP, DP a.s. | July 16th - Aug. 23rd 2008 | underground services reconstruction, cyclepass construction, road reconstruction, TT | complete closure of the tunnel | high - overloading of diverted routes | 2 DP and PPD priority 1
4 | Seifertova and Taboritska Str., Olsanske Square | 3 | DP a.s. | June 10th - July 8th 2008 | panels and track replacement | complete closure in both directions, Olsanske Square - 1 lane preserved | high - overloading of diverted routes | 3, DP priority 1
5 | Olsanska Str. Between Osanske Square and Zelivskeho | 3 | DP a.s. | July 8th - Aug. 25th 2008 | tram line repairs | closure of left lane in the outward direction from the city centre, restricted parking | low - even the capacity of one lane is sufficient | 3, DP priority 1
6 | Videnska Str. Between U Krcskeho Nadrazi Str. and Jizni Spojka | 4 | DP a.s. | Aug. - Oct. 2008, 2 months | metro track siding bridge reconstruction | restriction in traffic lanes, closure of 1 lane only at weekends | medium - lower capacity of the road | 3
7 | Modranska Str. In the outward direction, between Branicka Str. and entry to Branik turn-around | 4 | DP a.s. | Oct. 29th - Nov. 19th 2008 | tram track arcs replacement | closure of right lane in place of works on TT, left lane without restricitons | medium -lower capacity of the road | 3
8 | K Barrandovu Str. between Geologicka and Pod Habrovou Str, bridge X 34 | 5 | TSK HMP | July 1st - Aug 17th 2008 | dilatation replacement | partial closure, 2+2 will be preserved (1lane in the opposite direction) | high - significant drop in capacity of an overloaded road. If possible - postpone until the opening of Prague city by-pass | 2 TSK priority 1
9 | Radlicka Str between Krizova Str and CSOB loop | 5 | DP a.s. PVS a.s. | May 1st - Aug 30th 2008 | tram line, gas line and header reconstruction | complete closure in the outward direction, diversion via Plzenska Str and Santoska | high - overloaded diverted routes | 1 unsatisfactory state
10 | Dobrisska Str between Zlichov underpass and bridge over Jinonice track behind the underpass, both directions | 5 | OMI MHMP | July 10th - Aug 7th 2008 | dilatation replacement | ½ closure, 2 lanes will be preserved | medium -lower capacity of the road | 3
11 | Evropska Str at Borislavka and Nad Dzbanem stops | 6 | DP a.s. | July - Aug 2008, 1 month | adjustement and widening of stops | narrowed left lanes in places of work | low - requirement of 2 narrowed lanes | 3 city district interest
12 | Patockova Str at Vozovna Stresovice stop | 6 | DP a.s. | July - Aug 2008, 1 month | adjustement and widening of stops | narrowed left lanes in places of work | low - requirement of 2 narrowed lanes | 3 city district interest
13 | Cancelled
14 | Belohorska Str at Vypich loop | 6 | DP a.s. | July - Aug 2008, 1 month | adjustment and widening of stops | narrowed left lanes in places of work | low - requirement of 2 narrowed lanes | 3 city district interest
15 | Belohorska Str between Vypich and Bolivarova Str | 6 | KC Vypich s.r.o. | July 5th - Aug 25th 2008 | road reconstruction, construction of subway under tram tracks | ½ closure, requirement of 2 lanes in each direction | medium -lower capacity of the road | 3
16 | Karlovarska Str between Slanska and Drnovska Str | 6 | TSK HMP | May - Aug 2009 | widening of the road, SSZ adjustment | traffic restrictions depending on the works. Complete closure was not accepted | medium -lower capacity of the road | 1 coordination with RDS, money SFDI
17 | Drnovska Str between Karlovarska and Netrebska Str | 6 | TSK HMP | May - June 2008 55 days | construction of road drainage | closure of half of the road, traffic only in the direction of Karlovarska Str | medium -lower capacity of the road | 1 coordination with RDS
18 | Milady Horakove Str between Svatovitska Str and Letenske Square, Patockova Str between Strahov Tunnel and Myslbekova Str | 6 | OMI MHMP | June 28th - March 2009 (construction without tram diversion will continue until 2011) | city by-pass construction, deepened ramps in Letna, relaying of underground services | Closure in the outward direction from the city centre, traffic led in the opposite direction,Na Valech Str and after widening Na Spejcharu Str into the centre, Spejchar - Stresovice tram line suspended ( substitute bus transport) | high - overloading of diverted routes | 1 construction of city by-pass interest HMP
19 | Valcikova - V Holesovickach elevated crossing (X 554) | 7 | TSK HMP | June 1st - Aug 24th 2008 in total 6 weeks | reconstruction of the lower construction of the bridge in the streets Valcikova - V Holesovickach | Phase I - closure of left half of the road in both directions, 2 lanes will be preserved in right half Phase II closure of right half of the road in both directions, 2 lanes will be preserved in left half | medium -lower capacity of the road | 3
20 | Veselska Str, Kbelska Str | 8 | OMI MHMP | July 2008 - June 2009 | gradual construction of MUK Liberecka in | ½ closure of Kbelska Str, two way traffic in the other half, closure Veselska, possibility to turn from Kbelska on the right to Letnany | high - overloading of diverted routes | 2
21 | Cinovecka Str ramps connection to Dablice | 8 | TSK HMP | July - Oct 2008 | ramp surface repairs | closure of individual lanes | medium -lower capacity of the road | 3
22 | Krizikova Str at crossroads with prvniho Pluku Str | 8 | TSK HMP | June - Aug 2008 | crossroad reconstruction | restriction, traffic preserved in one lane for each direction | medium -lower capacity of the road | 3
23 | Jizni Spojka (South Connecting Rd) Zahradni Mesto exit - Cable Bridge | 10 | TSK HMP | July - Aug 2008 | dilatation and road surface repairs | closure of 1 lane, two way traffic in 2nd lane | high - significant drop in road capacity | 2
24 | Kolbenova Str between Zaluzanska and Slevacska Str | 14 | TSK HMP | July - Aug 2008 26 days | road reconstruction | ½ closure, one direction via diverted route | high - overloading of diverted routes | 1 money SFDI
25 | Prumyslova Str between Podebradska - bridge over Rokytka | 14 | TSK HMP | July - Aug 2008 | road reconstruction | partial closure, 1 lane always preserved | high - significant drop in road capacity | 3
26 | Ceskobrodska Str at crossroads with Lomnicka Str | 14 | Skanska a.s. | Aug 23rd 24th (weekend) | widening of road, crossroad adjustment | closure in the outward direction from the city centre, diverted route via Prumyslova, Sterboholska Spojka | high - overloading of diverted routes | 3
27 | Prazska - Svehlova crossroads | 15 | OMI MHMP | May 2nd - Aug 31st 2008 | crossroad reconstruction, relaying of underground services | complete closure of Prazska Str, both directions via diverted routes | high - overloading of diverted routes | 1 city district interest
28 | Brezany Valley before Komoranska Str | 16 | OMI MHMP | June 6th - July 18th | sewerage construction in area of Zavist | ½ closure, requirement of one way traffic from Zavod Miru Bridge, not SSZ shuttle traffic | high - significant overloading of diverted routes | 3 money from SFZP
29 | Novopacka Str between Bystra Str and CD underpass, ku Horni Pocernice | 20 | OMI MHMP | July - Nov 2008, closure of 1 lane during summer holiday only | connection with Vysocanska Radial | closure of right lane in the inward direction to the city centre, 2 lanes from Prague and 1 to Prague | high - significant drop in road capacity | 3
Legend
| traffic impact |  |  | restrictions extent
| high impact on traffic |  |  | complete closure
| medium impact on traffic |  |  | one way closure
work on important roads with low impact on traffic